## Project Risks
# | Status | Risk Description | Strategy | I | P | E | Risk owner | Budget (h) | Mitigation Plan | Corrective actions | Domain (Class,Element,Attribute)
| Planned | Нестача часу | Mitigation | 0.4 | 0.8 | 0.32 | Пащенко. М | 0 | Запланувати більше часу на виконання задач і передбачити запас часу на випадок форс-мажору | none | Program Constraints / Resources / Schedule
| Planned | Нестача трудових ресурсів | Avoidance | 0.4 | 0.8 | 0.32 | Порхун К. | 0 | Розробити план розподілення ресурсів | none | Program Constraints / Resources / Staff
| Planned | Розростання обсягу проекту | Mitigation | 0.1 | 0.1 | 0.01 | Пащенко М. | 0 | Зафіксувати об'єм проекту шляхом створення чітких параметрів для нього | none | Program Constraints / Resources / Facilities
| Analyzed | Пандемія | Acceptance | 0.1 | 0.2 | 0.02 | Чорноморець М. | 0 | none | none | Program Constraints / Other
| Identified | активні бойові дії | Mitigation | 0.8 | 0.4 | 0.32 | Музичина. А | 300 | Мати запас часу | none | Program Constraints / Other
| Identified | відключення електроенергії | Mitigation | 0.1 | 0.8 | 0.08 | Андресюк Д. | 100 | Мати запас часу | none | Program Constraints / Other
| Identified | Відсутність робочої взаємодії із замовником | Mitigation | 0.4 | 0.8 | 0.32 | Порхун К. | 10 | Використовувати спільні платформи та інструменти, забезпечувати своєчасне інформування замовника про стан проекту, визначати конкретних відповідальних осіб у команді розробників та в замовника для забезпечення чіткої комунікації | none | Development Environment / Work Environment / Communication
| Identified | Невизначеність вимог замовника | Mitigation | 0.4 | 0.8 | 0.32 | Порхун К. | 10 | Регулярна комунікація з замовником, розробка детального технічного завдання | none | Development Environment / Work Environment / Communication
| Identified | Впав сервер | Acceptance | 0.8 | 0.1 | 0.08 | Музичина. А | 20 | Моніторинг сервера | none | Development Environment / Development System / Reliability
| Identified | Впала база даних | Mitigation | 0.8 | 0.1 | 0.08 | Музичина. А | 20 | Моніторинг бази даних та створення резервної копії даних | none | Development Environment / Development System / Reliability
| Identified | Впав веб-сервер | Mitigation | 0.8 | 0.1 | 0.08 | Чорноморець М. | 20 | Використання багатопотокової архітектури, моніторинг сервера, використання балансувальників навантаження | none | Development Environment / Development System / Reliability
| Identified | Помилка розробників | Mitigation | 0.4 | 0.2 | 0.08 | Чорноморець М. | 50 | Навчання розробників,код-рев'ю, тестування, автоматизація процесів розробки | none | Product Engineering / Engineering Specialties / Human Factors
| Identified | Взлом сервера | Avoidance | 0.8 | 0.1 | 0.08 | Пащенко М. | 50 | Моніторинг сервера, Регулярне оновлення програмного забезпечення, Використання багатофакторної аутентифікації, Резервне копіювання даних. | none | Product Engineering / Engineering Specialties / Security
0
0
Note on D1: EugeneM: Mitigation Strategy
Note on E1: EugeneM: Impact
Note on F1: EugeneM: Probability
Note on G1: EugeneM: Exposure
Note on J1: EugeneM: Описание конкретных действий выполняемых в рамках выбранной стратегии (Strategy)

## Scales
Impact Scale | Very Low | Low | Moderate | High | Very High
| 0.05 | 0.1 | 0.2 | 0.4 | 0.8
Probability Scale | 0.1 | 0.3 | 0.5 | 0.7 | 0.9
Mitigation Strategy | Avoidance | Mitigation | Transference | Acceptance
RiskStatus | Identified | Analyzed | Planned | Handled | Occurred

## Risk Domains
Code | Domain
1.1.1 | Product Engineering / Requirements / Stability
1.1.2 | Product Engineering / Requirements / Completeness
1.1.3 | Product Engineering / Requirements / Clarity
1.1.4 | Product Engineering / Requirements / Validity
1.1.5 | Product Engineering / Requirements / Feasibility
1.1.6 | Product Engineering / Requirements / Precedent
1.1.7 | Product Engineering / Requirements / Scale
1.2.1 | Product Engineering / Design / Functionality
1.2.2 | Product Engineering / Design / Difficulty
1.2.3 | Product Engineering / Design / Interfaces
1.2.4 | Product Engineering / Design / Performance
1.2.5 | Product Engineering / Design / Testability
1.2.6 | Product Engineering / Design / Hardware Constraints
1.2.7 | Product Engineering / Design / Non-Developmental Software
1.3.1 | Product Engineering / Code and Unit Test / Feasibility
1.3.2 | Product Engineering / Code and Unit Test / Unit Test
1.3.3 | Product Engineering / Code and Unit Test / Coding/Implementation
1.4.1 | Product Engineering / Integration and Test / Environment
1.4.2 | Product Engineering / Integration and Test / Product
1.4.3 | Product Engineering / Integration and Test / System
1.5.1 | Product Engineering / Engineering Specialties / Maintainability
1.5.2 | Product Engineering / Engineering Specialties / Reliability
1.5.3 | Product Engineering / Engineering Specialties / Safety
1.5.4 | Product Engineering / Engineering Specialties / Security
1.5.5 | Product Engineering / Engineering Specialties / Human Factors
1.5.6 | Product Engineering / Engineering Specialties / Specifications
1.0.0 | Product Engineering / Other
2.1.1 | Development Environment / Development Process / Formality
2.1.2 | Development Environment / Development Process / Suitability
2.1.3 | Development Environment / Development Process / Process Control
2.1.4 | Development Environment / Development Process / Familiarity
2.1.5 | Development Environment / Development Process / Product Control
2.2.1 | Development Environment / Development System / Capacity
2.2.2 | Development Environment / Development System / Suitability
2.2.3 | Development Environment / Development System / Usability
2.2.4 | Development Environment / Development System / Familiarity
2.2.5 | Development Environment / Development System / Reliability
2.2.6 | Development Environment / Development System / System Support
2.2.7 | Development Environment / Development System / Deliverability
2.3.1 | Development Environment / Management Process / Planning
2.3.2 | Development Environment / Management Process / Project Organization
2.3.3 | Development Environment / Management Process / Management Experience
2.4.1 | Development Environment / Management Methods / Program Interfaces
2.4.2 | Development Environment / Management Methods / Monitoring
2.4.3 | Development Environment / Management Methods / Personnel Management
2.4.4 | Development Environment / Management Methods / Quality Assurance
2.4.5 | Development Environment / Management Methods / Configuration Management
2.5.1 | Development Environment / Work Environment / Quality Attitude
2.5.2 | Development Environment / Work Environment / Cooperation
2.5.3 | Development Environment / Work Environment / Communication
2.5.4 | Development Environment / Work Environment / Morale
2.0.0 | Development Environment / Other
3.1.1 | Program Constraints / Resources / Schedule
3.1.2 | Program Constraints / Resources / Staff
3.1.3 | Program Constraints / Resources / Budget
3.1.4 | Program Constraints / Resources / Facilities
3.2.1 | Program Constraints / Contract / Type of Contract
3.2.2 | Program Constraints / Contract / Restrictions
3.2.3 | Program Constraints / Contract / Dependencies
3.3.1 | Program Constraints / Program Interfaces / Customer
3.3.2 | Program Constraints / Program Interfaces / Associate Contractors
3.3.3 | Program Constraints / Program Interfaces / Subcontractors
3.3.4 | Program Constraints / Program Interfaces / Prime Contractor
3.3.5 | Program Constraints / Program Interfaces / Corporate Management
3.3.6 | Program Constraints / Program Interfaces / Vendors
3.3.7 | Program Constraints / Program Interfaces / Politics
3.0.0 | Program Constraints / Other